## Sheet1
| S1 | S2 | S3 | S4 | O1 | O2 | O3 | O4 | N1 | N2 | N3 | N4 | D1 | D2 | D3 | D4 | J1 | J2 | J3 | J4 | F1 | F2 | F3 | F4 | M1 | M2 | M3 | M4 | A1 | A2 | A3 | A4
Background | bar: O1 to O4
Ownership | bar: O2
Any Needed NDA | bar: O2 to O3
Use Cases | bar: O3 to O4
Initial Stories | bar: O4 to N1
Stories | bar: N2 to N3
TPS Reports | bar: N1 to D4
Spikes | bar: N3 to D4
Platform Choice Hardware/OS | bar: O2
Resources Acquired | bar: N1 to N4
Version Control Standard | bar: N2 to D1
Source Directory Design | bar: N2 to D2
Demonstration Procedures | bar: D1 to D4
Language Choice | bar: O2 to N3
Database Choice | bar: O2 to N4
Database Design and Access | bar: N3 to D4
IDE Choices | bar: O3 to O4
Programming Standards | bar: N1 to N4
Framework Choices | bar: N1 to N4
Unit Testing Standards | bar: N1 to N4
System Testing Standards | bar: N1 to N4
Documentation Standards | bar: N2 to D1
Automation Standards | bar: N1 to D4
Client Demonstrations and Feedback | bar: O2 to D4
Mid Project Evaluation Meeting | bar: D1 to D2
CORE Complete | bar: O2 to D2
Maintenance Documentation
User Documentation
Security Assurance